## Test Execution Report
Test Execution Report ¦ Final result: 224/224 PASS (100%)
Category | Details
Total test cases | 224
Executed | 224
Not executed | 0
Passed | 224
Failed | 0
Skipped | 0
Pass rate | 100%
Total defects found historically | 8
Open defects | 0
Severity of historical defects | 2 Critical, 3 High, 2 Medium, 1 Low
Test scope | 217 Bruno API regression tests and 7 Selenium UI tests
Key observation 1 | All 217 Bruno API tests and all 7 Selenium UI tests passed.
Key observation 2 | Selenium tests cover authentication, dashboard sorting/filtering controls and goal creation modal fields.
Key observation 3 | The admin creation test was a rerun after the user already existed; its first run returned 201 and passed.
Risk / impact | No open Critical or High defects remain in the final test result.
Recommendation | Repeat the regression suite with a clean test database after deployment.
Overall status | PASSED
Historical defects - all resolved
Bug ID | Title | Related SCRUM story | Priority | Severity | Description | Final status
SCRUM-23 | Tikslo kūrimo problemos | SCRUM-4 / SCRUM-5 | Medium | High | Per ilgas title, 0 arba neigiama suma, praeities data | Resolved
SCRUM-22 | Filtrų ir kalendoriaus problemos | SCRUM-7 | Medium | Medium | Kalendorius dingsta, filtrai buvo netvarkingi | Resolved
SCRUM-21 | Rūšiavimo indikacijos problema | SCRUM-8 | Medium | Low | Trūko ascending/descending indikacijos | Resolved
SCRUM-20 | Depozito sumų validacijos problemos | SCRUM-12 | Medium | High | Leido viršyti wallet arba tikslo sumą, nerodė klaidų | Resolved
SCRUM-19 | Administratoriaus prieigos apribojimai | SCRUM-14 | Medium | Critical | Neteisinga prieigos kontrolė | Resolved
SCRUM-18 | Registracijos dublikato apdorojimas | SCRUM-2 | Medium | High | Registracijos forma galėjo pakibti su dublikatais | Resolved
SCRUM-17 | Deposit API autorizacija | SCRUM-12 | Medium | Critical | Deposit endpointų autorizacijos problema | Resolved
SCRUM-11 | Registracijos laukų tarpai | SCRUM-2 / SCRUM-3 | Medium | Medium | Registracijos laukai priėmė tik tarpus | Resolved

## Test Summary Report
Test Summary Report ¦ MySavings ¦ 224/224 PASS (100%)
Field | Value
Project name | MySavings app
Test phase | Final API and UI regression testing
Total test cases | 224
Passed test cases | 224
Failed test cases | 0
Skipped test cases | 0
Pass rate | 100%
Total defects found historically | 8
Open defects | 0
Test execution environment | Windows 11 Pro, Chrome 149.0.7827.54, Bruno 3.4.2, MySQL
Overall status | PASSED
Comments / notes | Final result: 217 Bruno API tests and 7 Selenium UI tests passed, 224/224 in total. The admin creation test returned 400 only on rerun after the user already existed; its first execution returned 201.

## Selenium Execution
Selenium UI Test Execution ¦ 7/7 PASS (100%)
Class | Test method | Scenario coverage | Result | Notes
AuthTest | validUserCanLogInAndLogOut | SC-AUTH-01, SC-AUTH-03 | PASS | Login and logout flow
AuthTest | emptyLoginFormShowsFieldValidation | SC-AUTH-05 | PASS | Required field messages
AuthTest | invalidCredentialsKeepUserOnLoginPage | SC-AUTH-02 | PASS | Stays on /login; asserts exact error message 'Failed to log in. Please check your email and password.'
AuthTest | registrationShowsPasswordMismatchValidation | SC-REG-05 | PASS | Password mismatch validation
DashboardTest | dashboardAllowsGoalSortSelection | SC-SORT-02 (partial) | PASS | Verifies selected sort option for all 4 values (newest/deadline/amount/progress), not result order
DashboardTest | dashboardAllowsNameFilter | SC-FILTER-03 (partial) | PASS | Verifies filter flow and dashboard remains loaded
GoalCreationTest | createGoalModalOpensWithRequiredFields | SC-GOAL-01 (partial) | PASS | Verifies modal fields, not final API creation